RESOLUTION  No.

#### OF THE BOARD OF SUPERVISORS OF THE COUNTY OF NEVADA

Resolution approving amendment NO. 2 to the Professional Services Contract between the County of Nevada and DUDEK for The COMMUNITY WILDFIRE PROTECTION PLAN UPDATE, iNCREASING THE CONTRACT nOT TO EXCEED AMOUNT BY $25,000.00 FROM A CONTRACT mAXIMUM OF $157,323.50 TO $182,323.50 AND authorizing the director of emergency services to execute the contract AMENDMENT

WHEREAS, the Office of Emergency Services is responsible for preparing and mitigating wildfire hazards in the County; and

WHEREAS, the County of Nevada has a severe and present danger of wildfire presenting a threat to public health and safety; and

WHEREAS, the Community Wildfire Protection Plan (CWPP) is a key planning tool to help prioritize wildfire mitigation action; and

WHEREAS, Community Wildfire Protection Plans should be updated periodically to reflect work that has been completed, and guide strategy for future work; and

WHEREAS, on May 23, 2023 the Board approved the contract between the County of Nevada and Dudek for the Community Wildfire Protection Plan Update for the term of May 23, 2023 through December 31, 2024 for the maximum amount of $156,031.00 through Resolution No. 23-232; and

WHEREAS, this contract maximum was subsequently increased to $157,323.50 through Resolution No. 24-473; and

WHEREAS, the intent of the effort is to deliver a final Community Wildfire Protection Plan that is place-based and reflective of the community that it serves; and

WHEREAS, County of Nevada requests the incorporation of additional edits to the draft plan based on internal and stakeholder input, community survey results, and the public feedback period; and

WHEREAS, the parties desire to amend the contract to address these needs for the final version of the plan:

- Increase the budget by $25,000.00 under “5.1 Draft CWPP” increasing the contract Not to Exceed amount from $157,323.50 to $182,323.50

NOW, THEREFORE, BE IT HEREBY RESOLVED by the Board of Supervisors of the County of Nevada, State of California, that the County hereby approves Amendment No. 2 to the Professional Services Contract between the County of Nevada and Dudek for the Community Wildfire Protection Plan Update increasing the contract Not to Exceed amount by $25,000.00 from a contract maximum of $157,323.50 to $182,323.50 and authorizes the Director of Emergency Services to execute the contract amendment.

Funding

0101-20702-414-3000	521520